## Sheet1
ITEM | PCB VERSION | Date | PRIORITY | Hardware / Software | ISSUE | STATUS
1 | 18.16 | 2022-02-06 | High | Hardware | Q5 overloaded and smoked, it is burned out. This part performs switching 5V0 to the 555 delayed start timer driven by the trigger P0-2, a 24VDC input. | see prob 1 and 2 in 18.17
2 | 18.16 | 2022-02-06 | High | Hardware | GP028 is a pin read that is read by the RP2040. This does not provide an input readable by the RP2040 when P0-2 is high. | see prob 1 and 2 in 18.17
3 | 18.16 | 2022-02-06 | High | Hardware | The Timer for C1-1 which is shifted by the delayed start timer does not appear to be working. | see DV_MR_rev_18.17_modbus_ADC_ 555 COILER TIMERS remove R359. change voltage divider. Shown in Prob 6
4 | 18.16 | 2022-02-06 | High | Hardware | GP15 Pin poutput does not trigger P0-2. | see prob 3
5 | 18.16 | 2022-02-06 | High | Hardware | LED for RST0 and RST1 does not iluminate when GP6 or GP7 is pulled high by RP2040. This indicates that the cap is not being reset on the peak hold knock sensor. | see prob 05 and prob 05A
6 | 18.16 | 2022-02-06 | High | Hardware | Based on RST0 and RST1 not working, it indicates that the cap is not being reset on the peak hold knock sensor. | must be tested. Break the bridge and set to PO-2, then test output with knock sensor plugged in.
7 | 18.16 | 2022-02-06 | High | Hardware | I2C Bus - 0x68, MCP-0650 not reachable with scanner. | replced with gy521 see prob 4
8 | 18.16 | 2022-02-06 | High | software | I2C Bus - 0x50, 24CAT512 EEPROM, not able to write integer. | Remove WP on CAT24C512 pin 7, see PROB 5
9 | 18.16 | 2022-02-06 | High | software | UART RS485 RTU Untested | needs client/save library to test. Master library ok. Need Client library.
10 | 18.16 | 2022-02-06 | high | software | SPI0 TCP test aditional function codes. | seems ok
11 | 18.16 | 2022-02-06 | Low |  | Increase eathernet clearance well on PCB for assembly of the W5100s-EVB-pico on the board.
12 | 18.16 | 2022-02-06 | Low |  | Increae the size of the Jumpers, jumpers are small for site soldering.
13 | 18.16 | 2022-02-06 | Low |  | Add 2 jumpers between the common/ground and SNS0+ and the second between common/ground and SNS1+, this is required if the RP2040 is used to read the sensors.
14 | 18.16 | 2022-02-06 | Low |  | Decrease the brightness of the white LED's | replace R296 with 1K, R75 with 1K, R298 with 2K, R76 with 10K, R362 with 2.4K, etc
15 | 18.16 | 2022-02-06 | Low |  | Correct Bottom Silk screen for the I2C addresses, swap 0x40 and 0x41.
16 | 18.16 | 2022-02-06 | Low |  | Change top silkscreen of ground to common / P0-3, to ensure a common connection to the power supply.
17 | 18.16 | 2022-02-06 | Low |  | Change top silkscreen of LED P0-2 from incorrect P1-1 to correct P0-2.
18 | 18.16 | 2022-02-07 | Low |  | Move max7219 display away from 4-20mA inputs.
19 | 18.16 | 2022-02-07 | Low |  | Check for more common External LED connectors (CONN-SMD_A2008WV-S-2P)
20 | 18.16 | 2022-03-19 | high | hardware | Change label of LED RST0 to RST1 and LED RST1 to RST0, this is for LED7 and LED15