## Sheet1
ITEM | PCB VERSION | Date | PRIORITY | ISSUE | STATUS
1 | 18.16 | 2022-02-06 | High | Q5 overloaded and smoked, it is burned out. This part performs switching 5V0 to the 555 delayed start timer driven by the trigger P0-2, a 24VDC input.
2 | 18.16 | 2022-02-06 | High | GP028 is a pin read that is read by the RP2040. This does not provide an input readable by the RP2040 when P0-2 is high.
3 | 18.16 | 2022-02-06 | High | The Timer for C1-1 which is shifted by the delayed start timer does not appear to be working.
4 | 18.16 | 2022-02-06 | High | GP15 Pin poutput does not trigger P0-2.
5 | 18.16 | 2022-02-06 | High | LED for RST0 and RST1 does not iluminate when GP6 or GP7 is pulled high by RP2040. This indicates that the cap is not being reset on the peak hold knock sensor.
6 | 18.16 | 2022-02-06 | High | Based on RST0 and RST1 not working, it indicates that the cap is not being reset on the peak hold knock sensor.
7 | 18.16 | 2022-02-06 | High | I2C Bus - 0x68, MCP-0650 not reachable with scanner.
8 | 18.16 | 2022-02-06 | High | I2C Bus - 0x50, 24CAT512 EEPROM, not able to write integer.
9 | 18.16 | 2022-02-06 | High | UART RS485 RTU Untested
10 | 18.16 | 2022-02-06 | high | SPI0 TCP test aditional finction codes.
11 | 18.16 | 2022-02-06 | Low | Increase eathernet clearance well on PCB for assembly of the W5100s-EVB-pico on the board.
12 | 18.16 | 2022-02-06 | Low | Increae the size of the Jumpers, jumpers are small for site soldering.
13 | 18.16 | 2022-02-06 | Low | Add 2 jumpers between the common/ground and SNS0+ and the second between common/ground and SNS1+, this is required if the RP2040 is used to read the sensors.
14 | 18.16 | 2022-02-06 | Low | Decrease the brightness of the white LED's
15 | 18.16 | 2022-02-06 | Low | Correct Bottom Silk screen for the I2C addresses, swap 0x40 and 0x41.
16 | 18.16 | 2022-02-06 | Low | Change top silkscreen of ground to common / P0-3, to ensure a common connection to the power supply.
17 | 18.16 | 2022-02-06 | Low | Change top silkscreen of LED P0-2 from incorrect P1-1 to correct P0-2.
18 | 18.16 | 2022-02-07 | Low | Move max7219 display away from 4-20mA inputs.
19 | 18.16 | 2022-02-07 | Low | Check for more common External LED connectors (CONN-SMD_A2008WV-S-2P)
20